## Work Plan and Project Overview
WORK PLAN
| House number | Starting date | Estimated Ending date | SQUARE PER HOUSE |  | Staff Name | DEMOLISING ROOF PAYMENT | #DAYS EXTENTION | Materials request | Consumable request
1 |  |  |  |  | C
W
A
This workplan has being read over, explained to, and after having understood the contents hereof the Parties signed and entered into on (date)_____May 8 2026________________(place)_____Red Cross Training Center_________________.
| Site Supervisor | Andre Haughton |  | Carpenter |  |  | Regional Site Supervisor

## Site Visits
Date of visit | Visit / Call | Technical Team Participants | Estimated % Completion | Status | # of Work Days | Issues / comments | Days Active
3
4

## Daily Site Log (hidden)
Date | Site | Workers Present | Work Done | Estimated advance | Materials Needed | Issues/Delays | Photos Taken | Technical Team
2026-04-15 | FLAN014 | 3 | Work in progress | 0% | None | None | Yes | Called in
2026-04-16 | FLAN014 | 3 | Work in progress | 0% | None | None | Yes | Called in
2026-04-17 | FLAN014 | 3 | Work in progress | 0% | Screws | Material Shortage | Yes | On site
2026-04-20 | FLAN014 | 3 | Work in progress |  | Lumber | Material Shortages | Yes | Called in

## Document Checklist
House Number | BOQ | Scope | Workplan | Time extension | Notice of completion | Monitoring Check List | KOBO
H1 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE

## Material request
DATE REQUEST
PARISH
CLUSTER
CARPENTER NAME
SUPERVISOR NAME
List of replacement of materials
Description of items | Quantity | Price | Location | Request Date | Date Need | Date received
Received by site supervisor
Date
Signature

## Consumables form
DATE REQUEST
PARISH
CLUSTER
CARPENTER NAME
SUPERVISOR NAME
List of replacement of consumables
Description of items | Quantity | Price | Location | Request Date | Date Need | Date received
Received by site supervisor
Date
Signature

## COM
[6 empty] | IN / OUT | IN | IN | IN | IN | IN | OUT | Total
[6 empty] | FROM / TO | Kingston JRC Warehouse |  |  |  |  | TO STORAGE | Materials
Date
| ROOFING MATERIALS |  |  |  | BOQ |  | DELIVERED | ADITIONALS | ADITIONALS | ADITIONALS | ADITIONALS | LEFTOVERS | Total
| Item | Size | Length | Unit | Quantity |  | Quantity | Quantity | Quantity | Quantity | Quantity | Quantity | Quantity
1 | Ridge beam | 2x8 | 18 | Piece
2 | Rafters/Collars | 2x6 | 12 | Piece
3 | Rafters/Collars | 2x6 | 14 | Piece
4 | Rafters/Collars | 2x6 | 16 | Piece
5 | Rafters/Collars | 2x6 | 18 | Piece
6 | Rafters/Collars | 2x6 | 20 | Piece
7 | Battens/Wall plate | 2x4 | 10 | Piece
8 | Battens/Wall plate | 2x4 | 12 | Piece
9 | Battens/Wall plate | 2x4 | 14 | Piece
10 | Battens/Wall plate | 2x4 | 16 | Piece
11 | Battens/Wall plate | 2x4 | 18 | Piece
12 | Battens/Wall plate | 2x4 | 20 | Piece
13 | Blocking board | 1x12 | 16 | Piece
14 | Fascia board | 1x8 | 16 | Piece
15 | Plywood T1-11 | 4'x8' |  | Piece
16 | Zinc galvanized (26 gauge) | 36" x 10' | 10 | Piece
17 | Zinc galvanized (26 gauge) | 36" x 12' | 12 | Piece
18 | Zinc galvanized (26 gauge) | 36" x 14' | 14 | Piece
19 | Zinc galvanized (26 gauge) | 36" x 16' | 16 | Piece
20 | Zinc galvanized (26 gauge) | 36" x 18' | 18 | Piece
21 | Zinc galvanized (26 gauge) | 36" x 20' | 20 | Piece
22 | Ridge cap (24 gauge) | 14" x 10' | 10 | Piece
23 | Flashing/Verge | 6" x 10' | 10 | Piece
24 | Screws (conc) | 3/16" | 3 1/4" | Piece
25 | Screws (wood) | #10 | 3" | Piece
26 | Screws (wood) | #10 | 4" | Piece
27 | Screws (zinc) |  | 2 1/2" | Piece
28 | Hurricane strap | H3 | Left&right | Piece
29 | Flat strap |  |  | Piece
30 | Bolt expansion anchor | 1/2" x | 5-1/2" | Piece
31 | Coiled strap | GA18 | 100'x1 1/4" | Piece
32 | Nails (galvanized) | #8 | 1 1/2" | pound
33 | Nails (galvanized) |  | 3" | pound
34 | Nails (galvanized) |  | 4" | pound
TOTAL COST ROOF
| Signature | Signature |  |  | Signature
| for acceptance of materials | for acceptance of materials |  |  | for deliver of materials
| JRCS | Beneficiary |  |  | Transport/Store
| AHaughton | AHaughton |  |  | AHaughton